CLUB QUICK START

Friends of Rotary

A governed 90-day club pilot

REVIEW STATUS Private District 9510 working draft. Clubs must obtain local board approval and confirm current District, insurance, privacy, safety and youth-protection requirements before use.

Companion to the Club Toolkit | Review edition 1.0 | 9 August 2026

Prepared for Rotary clubs across District 9510. Designed for flexible, respectful participation without implying Rotary membership.

90-DAY OUTCOME

# Pilot one safe, meaningful participation pathway

At day 90, the club should have a board-approved model, at least two complete opportunity briefs, trained coordinators, a working privacy and follow-up process, participant feedback and a documented continue/improve/pause/close decision.

STOP CONDITION Do not invite Friends while ownership, safety, safeguarding, privacy, insurance or a real opportunity remains unresolved.

| Phase | Outcome | Evidence |
| --- | --- | --- |
| Days 1-15 - Decide | Approve purpose, boundaries, roles and release gates. | Board minute; accountable owner; policy questions logged and closed. |
| Days 16-30 - Design | Prepare two meaningful opportunities and the participant journey. | Opportunity briefs; invitation; collection notice; induction and follow-up. |
| Days 31-60 - Pilot | Invite a small, suitable group and deliver supported activities. | Human fit checks; attendance; issue route; thank-you and experience pulse. |
| Days 61-90 - Improve | Review category-level evidence and decide the next state. | 30/60/90 review; corrections; data action; next review date. |

PHASE 1 - DAYS 1-15

# Decide and govern

[ ] State the community and participation problem the model will solve.

[ ] Approve Friend status and the boundary from active or honorary membership.

[ ] Appoint board sponsor, coordinator, opportunity owners, safeguarding contact, privacy/data owner and backup.

[ ] Confirm current District, insurer, privacy, safety and youth-protection requirements.

[ ] Choose the monitored contact channel and record response ownership.

[ ] Approve collection, access, retention, deletion and withdrawal rules.

[ ] Set the day-30, day-60 and day-90 review dates now.

## Gate to phase 2

READY WHEN The board decision is recorded, every accountable role is filled, unresolved controls have owners and due dates, and no public invitation has been issued.

PHASE 2 - DAYS 16-30

# Design real opportunities

[ ] Create two opportunity briefs with purpose, task, commitment, place/access, support, safety, costs and follow-up.

[ ] Check that roles are meaningful and do not inappropriately replace paid work.

[ ] Resolve screening, supervision and partner controls before youth-related activity.

[ ] Prepare transparent invitation, welcome, reminder, induction, thank-you and withdrawal messages.

[ ] Test the expression-of-interest form for minimum data and a complete collection notice.

[ ] Practice the human fit check and a respectful 'no current match' response.

[ ] Have one person outside the project review the experience for clarity and accessibility.

PHASE 3 - DAYS 31-60

# Pilot with care

- Start small: invite only as many Friends as the named supervisors can support well.

- Respond personally, confirm fit and send the complete opportunity brief before acceptance.

- Resolve access, equipment, consent and screening for the specific activity.

- Welcome by name, orient to purpose, explain boundaries and identify who can help.

- Close the activity clearly, account for participants and route any issue immediately.

- Thank each Friend, ask the three-question pulse and record only the chosen next step.

- At day 60, correct weak opportunities or pause unsafe/unowned activity.

## Pilot pulse

| Question | Category-level result | Action |
| --- | --- | --- |
| Clear expectations and contact? | [Yes / partly / no] | [Owner and due date] |
| Useful, safe and welcomed? | [Yes / partly / no] | [Owner and due date] |
| Keep/change/follow up? | [Themes only] | [Owner and due date] |

PHASE 4 - DAYS 61-90

# Review and choose the next state

[ ] Close every outstanding safety, conduct, privacy or follow-up action.

[ ] Review time to response, time to opportunity, brief completeness and experience pulse.

[ ] Confirm communication preferences, withdrawal requests and data deletion actions were honoured.

[ ] Ask coordinators whether workload, backup and tools are sustainable.

[ ] Record what changed because Friends provided feedback.

[ ] Choose continue, improve, pause or close; record evidence and responsibilities.

[ ] Approve the next review date before expansion.

## Day-90 decision

| Decision | [Continue / improve / pause / close] |
| --- | --- |
| Evidence | [Category-level evidence] |
| Corrections | [Action, owner, due date] |
| Data action | [Delete / de-identify / retain under approved rule] |
| Next review | [Date] |
| Approved by | [Board / authorised role] |

SUCCESS A trustworthy Friend experience is the success: useful contribution, clear support, safe participation, respected choices and honest follow-up. Membership interest is optional and self-selected.